## Sheet1
	Use-Case Points Estimation Method
				(implemented by Solms)

Actor compexity	Weight	NumActors		Technical Complexity Factor	Weight	Value
Simple	1	1		Performance	2	4	8
Average	2	0		Scalability	2	3	6
Complex	3	1		Stability/availability/reliability	2	5	10
Unadjusted Actor Weight		4		Distributed system	2	4	8
				Portability	2	3	6
Use case complexity	Weight	NumUseCases		Modifiability	1	4	4
Simple	5	7		Usability	1	5	5
Average	10	1		Integrability	1	2	2
Complex	15	2		Auditability/monitorability	1	4	4
Unadjusted Use Case weight		75		Security	1	2	2
				User training facilities	1	4	4
Unadjusted Use Case Points		79		Installability	0.5	5	2.5
				Technical Complexity Factor		1.22
Environmental factor	Weight	Value
Stable requirements	2	2	4	1
Process experience	1.5	4	6	0
Application experience	0.5	3	1.5	0
OO experience	1	5	5	0
Difficult language	-1	1	-1	0
Lead analyst capability	1	5	5	0
Motivated team	1	5	5	0
Part time workers	-1	0	0	0
Environmental factor		0.64

Adjusted Use Case Points		60.95		Calibration factors
				min no environmental risks	max	hours/UCP
No of environmental risk areas		1		0	2	20	TRUE	20
				3	4	28	FALSE	0
Person hours/use case point		20		5	10	36	FALSE	0

Person hours		1219.01
Person days		152.38
Person weeks		30.48

Average hourly rate		R300.00

Project cost estimate		R365,702.85